## Sheet1
Number	Task name	Start date	Time(hours)
1	Literature Survey	5/1/2020	54
2	Creation of the Gannt chart and Milestones for the project	17/1/2020	22
3	Research into existing Velocity prediction programs	22/1/2020	24
4	Research into the APIs for the project	29/1/2020	18
5	Meetings with naval-architecture specialist	8/2/2020	8
6	Requirement Specification	19/2/2020	10
7	Requirement Prioritization	22/2/2020	5
8	Use Case Diagram	26/2/2020	3
9	Robustness Diagram	28/2/2020	4
10	Class Diagram	4/3/2020	12
11	Interface Design	9/3/2020	10
12	Implementation of initial hydrodynamic functions	13/3/2020	24
13	Testing and debugging of hydrodynamic functions	3/4/2020	10
14	Implementation of aerodynamic functions	7/4/2020	32
15	Testing and debugging of aerodynamic functions	17/4/2020	10
16	Implementation of extra features for the hydrodynamic module	21/4/2020	20
17	Inclusion of the rudder parameters in the hydrodynamic calculations	27/4/2020	10
18	Testing and debugging of hydrodynamic functions with added features	1/5/2020	17
19	Implementation of the equilibrium module	5/5/2020	20
20	Testing and debugging of equilibrium module	11/5/2020	10
21	Development of the front-end of the system	15/5/2020	23
22	Testing and debugging of the front-end	22/5/2020	11
23	Optimising system functions	26/5/2020	17
24	Analysis of the results	1/6/2020	27
		Total:	401